## Overview
PAS — Test Checklist (June 6 Build)
Founder-facing QA pass. Only confidently-shipped functionality is included.
Prepared | 2026-05-31
Target build date | June 6, 2026
Customer app tests
Merchant app tests
P0 — Blocker if failing
P1 — Important but not blocking
Tests passed
Tests failed
Tests blocked
Tests not yet run
LEGEND
P0 | Blocker. Must pass before shipping the June 6 build.
P1 | Important. Should pass; ship with workarounds if needed.
P2 | Polish. Nice-to-have for this build.
Pass | Founder ran the test and it worked end-to-end.
Fail | Founder ran the test and observed broken behavior — log details in Notes.
Blocked | Cannot test right now (missing dependency, infra, etc.).
N/A | Not applicable to this device / scenario.
Not Tested | Default — has not been attempted yet.
OUT OF SCOPE FOR THIS PASS
• | Exchange / Return / Cancel / Reschedule flows (WS2 — not yet built).
• | Settlement / Payout History screen (blocked on payout-vendor selection).
• | Wati "Chat with us" support button (component exists, not yet placed in a screen).
• | Sentry crash reporting (DSN not configured; not in current native build).
• | Auto-refund on confirmed orphaned payments (code paths commented; not enabled).
• | Real merchant payout math (display rounded; underlying formula is still a placeholder × 0.98).
• | Scheduled / return / refund notifications (Phase 2 + 3).
• | KYC / GST verification vendor integration.
• | Cross-merchant analytics / Reports / Multi-admin RBAC / Audit log.

## Customer App
Customer App — Test Checklist
Run on a TestFlight build. Use a real Indian phone for OTP; Razorpay in test mode.
Test ID | Module | Scenario | Steps | Expected Result | Priority | Status | Notes (founder)
LOGIN & ONBOARDING
C-001 | Login & Onboarding | First-time onboarding screens render | 1. Install fresh, open app 2. Tap through the onboarding screens to the end 3. Tap "Get Started" | Reaches the home feed or location prompt without crash. Onboarding does not show again on relaunch. | P0 | Not Tested
C-002 | Login & Onboarding | Phone-OTP login via WhatsApp (Wati) | 1. Tap profile / cart → triggers auth 2. Enter your Indian phone number 3. Tap Send OTP 4. Receive 6-digit code on WhatsApp 5. Enter code → tap Verify | OTP message arrives within ~10s. Verification logs you in and returns to the previous screen. | P0 | Not Tested
C-003 | Login & Onboarding | OTP repeated requests are no longer banned | 1. Request OTP 2. Immediately request a 2nd, 3rd, 4th OTP (back-to-back) | Each request goes through. NO "Too many OTP requests. Please wait 10 minutes." error appears. | P0 | Not Tested
C-004 | Login & Onboarding | Wrong OTP attempts are limited per OTP record | 1. Request OTP 2. Enter 5 incorrect codes | After the 5th wrong attempt the API returns "Too many incorrect attempts. Please request a new OTP." Requesting a fresh OTP resets the limit. | P1 | Not Tested
C-005 | Login & Onboarding | Profile setup after first login | 1. First-time user finishes OTP 2. Asked to set name / email | Profile setup screen appears. Saving navigates to home feed. Re-login skips profile setup. | P1 | Not Tested
DISCOVERY & BROWSE
C-006 | Discovery & Browse | Manual location selection | 1. Tap location pill at top 2. Search for a known address in Hyderabad (e.g. "Banjara Hills") 3. Pick an autocomplete result | Location is set, nearby stores list refreshes to that locality. | P0 | Not Tested
C-007 | Discovery & Browse | Use current device location | 1. Tap location pill 2. Tap "Use my current location" 3. Allow OS permission | Coordinates are captured and nearby stores within 10 km are listed. | P0 | Not Tested
C-008 | Discovery & Browse | Nearby stores returned by API | 1. Set a location near any live test storefront (e.g. Folli Banjara at ~17.4338, 78.4318) 2. Wait for the home feed to load | At least one store card appears in the "Nearby" / Pickup feed. | P0 | Not Tested
C-009 | Discovery & Browse | Open a storefront and view products | 1. Tap any store card 2. Scroll product list / categories | Storefront opens with products grouped by category. No blank state on a populated store. | P0 | Not Tested
C-010 | Discovery & Browse | Pickup-only vs dining stores show correct UI | 1. Open a pickup-only store (e.g. pharmacy) 2. Open a dining store | Pickup store: no Dine-in / Table Booking options. Dining store: Dine-in + Slots options visible. | P1 | Not Tested
C-011 | Discovery & Browse | Product detail screen | 1. From a storefront, tap any product card | Detail screen shows image, price, description, Add-to-cart CTA. | P1 | Not Tested
CART
C-012 | Cart | Add to cart from storefront | 1. Tap "+" on a product in a storefront 2. Open Cart tab | Item appears in cart with correct price and quantity 1. Floating cart band at the bottom updates. | P0 | Not Tested
C-013 | Cart | Change quantity in cart | 1. In Cart, tap + and − on an item | Quantity, item subtotal, and cart total update correctly. Going to 0 removes the item. | P0 | Not Tested
C-014 | Cart | Cart persists across app relaunch | 1. Add items to cart 2. Force-quit the app 3. Reopen | Cart contents are intact. | P1 | Not Tested
PICKUP CHECKOUT
C-015 | Pickup Checkout | Open Pickup Checkout from cart | 1. With items in cart, tap Checkout | Checkout screen loads. Shows Pickup Locations, Select Pickup Time, Picking Up For, Bill Details, Place Order CTA. | P0 | Not Tested
C-016 | Pickup Checkout | Select pickup time | 1. On Checkout tap "Select Pickup Time" or "Change" 2. Pick an available slot | Slot is shown on the row. Place Order remains enabled. | P0 | Not Tested
C-017 | Pickup Checkout | Picking Up For: Myself vs Someone Else | 1. Toggle between Myself / Someone Else 2. For Someone Else, type a name + mobile | Toggle works; Someone Else mode shows name + mobile inputs. Place Order is enabled when filled. | P1 | Not Tested
C-018 | Pickup Checkout | Bill Details math | 1. Add 1+ items totaling ₹X 2. Go to Checkout | Item Total = sum of items, To Pay = Item Total + GST − Discount. Numbers are clean (no float spill). | P0 | Not Tested
C-019 | Pickup Checkout | Place pickup order via Razorpay | 1. On Checkout tap Place Order 2. Complete Razorpay flow (UPI or card test mode) | Razorpay sheet opens, payment succeeds, order is confirmed, redirected to a confirmation/Orders screen. | P0 | Not Tested
DINING CHECKOUT
C-020 | Dining Checkout | Open Dining Checkout | 1. On a dining store, tap Book / Proceed → Dining Checkout | Dining Checkout shows guests, arrival slot, bill summary, Place Order CTA. | P0 | Not Tested
C-021 | Dining Checkout | Place a dining order | 1. Pick a slot 2. Confirm guest count 3. Tap Place Order, finish Razorpay | Order is placed; confirmation visible. | P0 | Not Tested
COUPONS
C-022 | Coupons | "Apply Coupon" row visible above Bill Details | 1. Go to Pickup Checkout 2. Look just above the red "Bill Details" header | A white row with the ticket icon and "Apply Coupon ›" is present. | P0 | Not Tested
C-023 | Coupons | "Apply Coupon" row also visible on Dining Checkout | 1. Go to Dining Checkout 2. Look in the order summary area | Same Apply Coupon row present and tappable. | P0 | Not Tested
C-024 | Coupons | Open the Apply-Coupon screen | 1. Tap the Apply Coupon row | Slide-in screen titled "Apply Coupon" with cart subtotal in the subheader, a code-entry input, "Best coupon" + "More offers" sections. | P0 | Not Tested
C-025 | Coupons | Coupon cards match the admin builder design | 1. Publish a coupon in admin (any theme + brand logo upload) 2. On the customer Apply-Coupon screen, find that coupon | The card renders with the same theme as admin (Modern = no side tab; Classic/Bold/Festive = side tab). Brand logo image renders correctly when uploaded. | P0 | Not Tested
C-026 | Coupons | Apply a coupon by tapping the card | 1. On Apply-Coupon screen, tap any eligible card | Returns to Checkout. Bill Details shows an "Offer Discount −₹X" line. Apply Coupon row now shows "✓ CODE applied — You saved ₹X" with a REMOVE button. | P0 | Not Tested
C-027 | Coupons | Apply via manual code entry | 1. On Apply-Coupon screen, type a valid coupon code 2. Tap APPLY | Same applied-state UX as C-026. | P1 | Not Tested
C-028 | Coupons | Invalid / non-existent code shows error | 1. Type a garbage code (e.g. ZZZZ123) 2. Tap APPLY | Inline error in red: "Invalid coupon code" (or similar). | P1 | Not Tested
C-029 | Coupons | Coupon below minimum order is rejected | 1. Pick a coupon with a min-order (e.g. ₹100) 2. Have cart below ₹100 3. Tap the card | Inline error: "Add ₹X more to use this coupon" (server-driven message). | P1 | Not Tested
C-030 | Coupons | Remove an applied coupon | 1. With a coupon applied, tap REMOVE on the row | Discount line disappears, To Pay returns to pre-discount total, "Apply Coupon ›" row returns. | P0 | Not Tested
C-031 | Coupons | Per-customer limit enforces on repeat use | 1. Apply a coupon with per-customer limit = 1, place + pay an order 2. Start a new order, try the same coupon | Second attempt is rejected with a "you have already used this coupon" style message. | P1 | Not Tested
ORDERS & TRACKING
C-032 | Orders & Tracking | Order appears in Your Orders after payment | 1. Place + pay any order 2. Open Your Orders | New order appears at top with correct items, total, store name. | P0 | Not Tested
C-033 | Orders & Tracking | Open Invoice from an order | 1. In Your Orders, tap a placed order | InvoiceModal opens showing seller block, GSTIN, pickup/dine-in branching. | P1 | Not Tested
C-034 | Orders & Tracking | Order status updates as merchant acts | 1. Place order 2. Have merchant accept / mark ready (or simulate) 3. Watch Your Orders | Status updates without manual refresh (Realtime). | P1 | Not Tested
NOTIFICATIONS
C-035 | Notifications | Notification bell + badge | 1. With unread notifications, look at the bell on home | Red badge with count visible. | P1 | Not Tested
C-036 | Notifications | Notifications screen lists events | 1. Tap the bell | List of recent notifications (order events) appears. | P1 | Not Tested
C-037 | Notifications | Push notification delivers to device | 1. Place an order that triggers a push (e.g. confirmed) 2. Background the app | Push notification appears on lock screen / banner. Tapping it opens the app. | P1 | Not Tested
PROFILE & SESSION
C-038 | Profile & Session | Session does NOT auto-logout on relaunch after hours | 1. Use the app, then close it 2. Wait several hours / overnight 3. Reopen | Still logged in; no forced re-login. (Verifies the refresh-rotation fix.) | P0 | Not Tested
C-039 | Profile & Session | Session survives background → foreground | 1. Background the app for 5+ min 2. Bring to foreground | Still logged in, no eviction to Auth. | P0 | Not Tested
C-040 | Profile & Session | Mid-session no spontaneous logout | 1. Use the app continuously for ~10 min | No spontaneous bounce to login. | P0 | Not Tested
C-041 | Profile & Session | Manual logout from Profile | 1. Profile → Sign Out | Logs out cleanly. Re-login via OTP works. | P1 | Not Tested

## Merchant App
Merchant App — Test Checklist
Run on a TestFlight build. Use a registered merchant phone for OTP.
Test ID | Module | Scenario | Steps | Expected Result | Priority | Status | Notes (founder)
LOGIN & SESSION
M-001 | Login & Session | Phone-OTP login via WhatsApp (merchant) | 1. On Merchant app login screen, enter a registered merchant phone 2. Tap Send OTP 3. Enter code received on WhatsApp | Login succeeds, lands on Dashboard. | P0 | Not Tested
M-002 | Login & Session | OTP back-to-back resend works (no ban) | 1. Tap Send OTP 2. Tap Send OTP again immediately 3. Repeat 4× total | Each send works. No "wait 10 minutes" error. | P0 | Not Tested
M-003 | Login & Session | Branch-level login (multi-branch merchants) | 1. For a merchant with multiple branches, log in 2. Select a branch when prompted | Lands on Dashboard of the chosen branch. Switching branches is possible from Settings. | P1 | Not Tested
M-004 | Login & Session | Session does NOT auto-logout on relaunch | 1. Close app overnight 2. Reopen | Still logged in; goes straight to Dashboard. | P0 | Not Tested
M-005 | Login & Session | Session survives background → foreground | 1. Background app for 5+ min 2. Foreground | Still logged in. | P0 | Not Tested
DASHBOARD
M-006 | Dashboard | Dashboard greeting + branch name | 1. Open Dashboard after login | Greeting (Good Morning/Afternoon/Evening) + branch name (e.g. "Clean cuts") appear at top. | P1 | Not Tested
M-007 | Dashboard | Online / Offline toggle | 1. Tap the Online / Offline pill at the top right | State flips; merchant becomes invisible to customers when Offline. | P0 | Not Tested
M-008 | Dashboard | Today's Orders count is correct | 1. Place a real order from customer app 2. Check Dashboard "Today's Orders" card | Number increments by 1. | P0 | Not Tested
M-009 | Dashboard | Pending / Completed counts | 1. Have one order accepted but not completed → "Pending" 2. Complete one → "Completed" | Cards update accordingly. | P1 | Not Tested
M-010 | Dashboard | Revenue tile shows today's gross | 1. After at least one completed order today | Revenue card shows ₹ amount equal to sum of completed orders today. | P1 | Not Tested
M-011 | Dashboard | Estimated Payout display formatting (no float spill) | 1. After at least one completed order | Estimated Payout shows a clean rupee amount with 2 decimals (e.g. ₹6.86). No long float like ₹6.85999... NOTE: display check only — the actual payout formula is still a placeholder. | P1 | Not Tested
ORDER FLOW
M-012 | Order Flow | Notification bell shows pending order count | 1. Customer places a new order | Bell badge increments on Dashboard. | P0 | Not Tested
M-013 | Order Flow | Accept an order request | 1. New order arrives, tap Accept (or in the Pending tab) | Order moves to Processing / Ready queue. Customer sees status update. | P0 | Not Tested
M-014 | Order Flow | Reject an order request | 1. New order arrives, tap Reject | Order removed from queue; customer receives notification. | P0 | Not Tested
M-015 | Order Flow | Order Ready + OTP verification | 1. On a Processing order, tap Mark Ready 2. When customer arrives, enter the 4-digit pickup OTP | Correct OTP marks order Completed. Wrong OTP shows error. | P0 | Not Tested
INVENTORY
M-016 | Inventory | Open Inventory list | 1. Tap Inventory in bottom nav | Product list loads with categories, in-stock states, and quick filter chips. | P0 | Not Tested
M-017 | Inventory | Filter Modal applies category / brand / availability | 1. In Inventory, tap the filter icon 2. Pick a category, brand, availability, apply | List filters down to matches. Chip indicator shows active filters. | P1 | Not Tested
M-018 | Inventory | Toggle a product Out of Stock | 1. Long-press or tap into a product 2. Toggle availability | Product greys out / shows out-of-stock badge. Customer app no longer shows it. | P0 | Not Tested
M-019 | Inventory | Add a product from global catalog | 1. Inventory → Add → Search a known catalog item 2. Set price + tap Add | Item appears in the merchant's inventory at the set price. | P1 | Not Tested
M-020 | Inventory | Add a custom product (not in global catalog) | 1. Inventory → Add Custom Product → fill fields, save | Custom product is created and appears in inventory. | P1 | Not Tested
M-021 | Inventory | AddMenuProductModal rejects duplicate name | 1. Try adding a menu item with a name already present | Error: "An item with this name already exists." (or similar) | P1 | Not Tested
BOOKINGS (DINING)
M-022 | Bookings (Dining) | Bookings screen loads | 1. On a dining merchant, open Bookings | Bookings list for today loads. | P0 | Not Tested
M-023 | Bookings (Dining) | Slot Config edits | 1. Open Slot Config 2. Change a slot capacity / time 3. Save | Save succeeds. Reopen confirms the new value. | P1 | Not Tested
PROFILE & SETTINGS
M-024 | Profile & Settings | Profile screen view | 1. Tap Settings → Profile (or profile icon) | Merchant name, phone, branch info displayed. | P1 | Not Tested
M-025 | Profile & Settings | Manual logout | 1. Settings → Sign Out | Returns to login. Re-login via OTP works. | P1 | Not Tested
NOTIFICATIONS
M-026 | Notifications | New-order push notification | 1. Background the app on merchant device 2. Customer places an order | Push notification appears on lock screen. Tap opens the merchant app on the order. | P0 | Not Tested
M-027 | Notifications | In-app notification list | 1. Tap the bell on Dashboard | Recent in-app notifications listed. | P1 | Not Tested